## Read Me - Structure
NOVAtech Inc. — Enterprise Risk Register
HOW THIS WORKBOOK IS STRUCTURED
Tab: Scales & Criteria | Defines what each Likelihood and Impact score MEANS, plus the risk appetite threshold. Scores without defined criteria are vibes — this tab is what makes every number in the register defensible.
Tab: Risk Register | The living document. One row per risk. Inherent score = risk before controls; Residual = after treatment. Score cells are formulas (L × I) and color-coded against appetite.
Tab: Heat Map | The 5×5 board-level view — inherent risk positions by Likelihood × Impact. This is what executives actually look at.
COLUMN ANATOMY | What job each register column does:
Risk ID | Stable reference (R-01...). Other documents (SoA, audit findings, incident reviews) cite these IDs — never renumber.
Risk Description | Written as event + consequence ('Phishing leads to credential compromise'), not a topic ('phishing'). A risk you can't describe as an event can't be scored.
Asset / Process | Links the risk to the asset inventory — what is actually at stake.
Existing Controls | What's in place TODAY. This is what separates inherent from residual thinking.
L / I (1-5) | Scored strictly against the Scales tab definitions. If you can't point at the definition, don't assign the number.
Inherent Score | Formula: L × I, before treatment. Color: red ≥12, amber 6-11, green <6.
Treatment | One of the four options: Mitigate, Transfer, Avoid, Accept. A register where everything says 'Mitigate' hasn't engaged with risk appetite — documented acceptance is a feature.
Treatment Actions | The concrete plan. Measurable endpoints, not intentions.
Risk Owner | A BUSINESS role, not 'the security team'. The business owns risk; security facilitates. Ownership is what makes deadlines enforceable.
Target Date / Status | Treatment is a project: it has a deadline and a state.
Residual L / I / Score | Re-scored assuming treatment completes. The gap between inherent and residual is the value the treatment buys.
Review Date | Risks change. A register nobody revisits is a museum.
APPETITE RULE | NOVAtech accepts residual risk ≤ 6. Anything above 6 after treatment needs escalation or further treatment. This single number is what turns the register from a list into a decision tool.

## Scales & Criteria
Scoring Scales & Risk Criteria
LIKELIHOOD SCALE
Score | Label | Definition
5 | Almost certain | Expected to occur within 12 months; occurs routinely in industry peers
4 | Likely | Will probably occur within 12-24 months; has occurred before
3 | Possible | Could occur within 2-3 years; industry incidents are common
2 | Unlikely | Not expected, but possible; would require unusual circumstances
1 | Rare | Exceptional circumstances only
IMPACT SCALE
Score | Label | Definition
5 | Severe | >$1M loss OR regulatory breach with reporting obligation OR >24h platform outage OR loss of major customer
4 | Major | $250K-$1M loss OR exposure of customer PII OR 8-24h platform outage OR contractual SLA breach
3 | Moderate | $50K-$250K loss OR internal data exposure OR 2-8h outage OR significant remediation effort
2 | Minor | $10K-$50K loss OR brief degradation OR contained single-team disruption
1 | Negligible | <$10K; absorbed within normal operations
RISK APPETITE
Residual risk ≤ 6 is acceptable. Residual > 6 requires further treatment or executive escalation. Score bands: 12-25 High (red), 6-11 Medium (amber), 1-5 Low (green).

## Risk Register
Risk ID | Risk Description | Asset / Process | Threat Source | Existing Controls | Likelyhood | Impact | Inherent Score | Treatment | Treatment Actions | Risk Owner | Target Date | Status | Res. L | Res. I | Residual Score | Review Date
R-01 | Phishing leads to credential compromise and unauthorized account access | M365 / all staff | External - criminal | Email filtering; MFA on ~88% of accounts | 4 | 4 | 16 | Mitigate | Enforce MFA tenant-wide; exceptions require CISO risk acceptance with expiry; quarterly phishing simulations | IT Manager | 2026-08-15 | In progress | 2 | 2 | 4 | 2026-10-01
R-02 | Exploitation of unpatched critical vulnerability on internet-facing application | Customer platform | External - criminal | Monthly scans; ad-hoc patching | 3 | 5 | 15 | Mitigate | SLA-based remediation (Critical=7d); CISA KEV monitoring; weekly external scans | Eng Lead | 2026-08-31 | In progress | 1 | 5 | 5 | 2026-10-01
R-03 | Misconfigured S3 bucket exposes customer PII | AWS storage | Internal - error | Manual configuration reviews | 3 | 5 | 15 | Mitigate | Org-wide S3 public-access block; CSPM tooling with alerting | Cloud Lead | 2026-09-15 | Open | 1 | 5 | 5 | 2026-10-01
R-04 | Terminated employee retains system access | IAM / HR process | Internal - process | Ticket-based deprovisioning | 4 | 3 | 12 | Mitigate | HRIS-triggered auto-deprovisioning; weekly reconciliation until delivered; quarterly access reviews | IT Manager | 2026-08-31 | In progress | 1 | 3 | 3 | 2026-10-01
R-05 | Ransomware encrypts endpoints and servers | Laptops / servers | External - criminal | EDR deployed; backups exist but untested | 3 | 5 | 15 | Mitigate | Quarterly restore testing; immutable backup tier; network segmentation for servers | IT Manager | 2026-09-30 | Open | 2 | 3 | 6 | 2026-10-01
R-06 | Critical SaaS vendor breach exposes MapleTech data | Payroll / CRM vendors | External - supply chain | Contracts only; no security assessment | 3 | 4 | 12 | Mitigate | TPRM program: vendor tiering, SOC 2 review, DPAs with breach-notification SLAs | GRC | 2026-09-30 | Open | 2 | 3 | 6 | 2026-10-01
R-07 | Departing sales staff exfiltrate CRM customer data | CRM data | Internal - malicious | Access logging | 3 | 3 | 9 | Mitigate | DLP rules on bulk exports; offboarding checklist; least-privilege CRM roles | Sales Ops | 2026-09-15 | Open | 2 | 2 | 4 | 2026-10-01
R-08 | PIPEDA non-compliance: no breach process or data inventory | Compliance | Regulatory | None formalized | 3 | 4 | 12 | Mitigate | Privacy program: data mapping, breach-response runbook, RROSH assessment template | GRC | 2026-08-31 | In progress | 1 | 4 | 4 | 2026-10-01
R-09 | Unauthorized or failed production change causes outage | Customer platform | Internal - process | Informal peer review | 4 | 3 | 12 | Mitigate | Formal change management; CAB for high-risk changes; documented rollback plans | Eng Lead | 2026-08-15 | In progress | 2 | 3 | 6 | 2026-10-01
R-10 | Loss or theft of unencrypted laptop containing customer data | Endpoints | External - opportunistic | Disk encryption on ~80% of fleet | 3 | 4 | 12 | Mitigate | Enforce FDE via MDM on 100% of fleet; monthly compliance verification | IT Manager | 2026-07-31 | In progress | 1 | 3 | 3 | 2026-10-01
R-11 | DDoS attack degrades customer platform availability | Platform availability | External - criminal | Basic CDN tier | 2 | 4 | 8 | Mitigate | Upgrade DDoS protection tier; response runbook | Cloud Lead | 2026-09-30 | Open | 1 | 4 | 4 | 2026-10-01
R-12 | Key-person dependency: single DevOps admin for production | Operations | Internal - structural | None | 3 | 3 | 9 | Mitigate | Cross-train second engineer; document runbooks; partial residual accepted | CTO | 2026-10-31 | Open | 2 | 3 | 6 | 2027-01-01
R-13 | Shadow IT: unapproved SaaS holding customer data | Data governance | Internal - process | None | 3 | 3 | 9 | Mitigate | SaaS discovery tooling; approval process embedded in AUP | GRC | 2026-09-30 | Open | 2 | 2 | 4 | 2026-12-01
R-14 | Expired TLS certificate takes down customer API | Platform | Internal - process | Manual renewal calendar | 2 | 3 | 6 | Mitigate | Automated certificate renewal with expiry monitoring and alerting | Eng Lead | 2026-08-15 | In progress | 1 | 2 | 2 | 2027-01-01
R-15 | Physical intrusion into HQ server closet | HQ infrastructure | External - opportunistic | Badge access; no production systems on site | 2 | 2 | 4 | Accept | Risk formally accepted: low residual, no production assets at HQ. Signed by CTO 2026-07-10; review annually | Facilities | — | Accepted | 2 | 2 | 4 | 2027-07-01
LEGEND: Yellow cells = scoring inputs (edit these, per Scales tab definitions). Score columns are formulas (L×I) — do not type over them. Color bands: red ≥12 High, amber 6-11 Medium, green ≤5 Low (appetite: residual ≤6).

## Heat Map
Inherent Risk Heat Map (Likelihood × Impact)
Cell shading = severity zone. IDs shown at inherent scores, before treatment.
Impact 5 |  |  | R-02 R-03 R-05
Impact 4 |  | R-11 | R-06 R-08 R-10 | R-01
Impact 3 |  | R-14 | R-07 R-12 R-13 | R-04 R-09
Impact 2 |  | R-15
Impact 1
| Likelihood 1 | Likelihood 2 | Likelihood 3 | Likelihood 4 | Likelihood 5